## Sheet1
Top Priorities Sprint1
Number | User Stories | Priority | Sprint
1 | As a user, I want to know the university team so that I can reach out to ask for help. | 1 | The list of top-priority user stories that were selected from the first sprint. These user stories should be worked on between the first and second sprint meetings.
2 | As a user, I want to be aware of the benefits of studying at this university so that the advantages encourage me to join.
3 | As a user, I want to see new positions on the websites so that I can find new job announcements.
4 | As a user, I need to be able to read the job description so I can know if it is related to my field or not.
5 | As a user, I need to see a form so I can submit my requirements for a job.
6 | As a user, I want a donation form from the university so I can support students that need financial help.
7 | As a user, I want the university website to be user-friendly so I can use the website easily.
8 | As a user, I want to see social media accounts so that I can follow the university pages.
9 | As a user, I want to see quotes so I can get motivated.
10 | As a user, I want to know about the university's privacy policy so that I can know about the limits and its policies to follow.
11 | As a user, I want to know the location of the university so that I can easily find the place.
Top Priorities Sprint 2
Number | User Stories | Priority | Sprint
1 | As a user, I want to see the website logo so I can know it by its logo to find it easily. | 2 | The list of top-priority user stories that were selected from the second sprint. These user stories should be worked on between the second and third sprint meetings.
2 | As a user, I should see university students' feedback about their experiences so that I can be encouraged to trust in joining the university.
3 | As a user, I want to have access to an important portals such as canvas and power campus so I could easily access the portal.
4 | As a user, I want to see important events at the university so that I can see students in outside academic activities.
5 | As a user, I want to see the rights to copy so that It helps to see if the website is valid.
6 | As a user, I want to know about the university's supporters so that I can know them.
7 | As a user, I want to see a portal to help me see my grades.
8 | As a user, I want to have contact with a mentor-student so I can seek help and know about his/her experience.
9 | As a user, I want to see icons so that it helps me understand the links.
10 | As a user, I want to search keywords so that I can easily find the information I need.
11 | As a user, As a user, I want to be able to see the recorded expert instructor so that it can help me in know how successful this university's instructors are.
Top Priorities Sprint 3
Number | User Stories | Priority | Sprint
1 | As a user, I want to see a record of the university so that it ensures I trust the university. | 3 | The list of top-priority user stories that were selected from the second sprint. These user stories should be worked on between the second and third sprint meetings as well.
2 | As a user, I want to access the online libraries' links so that I could read books and journals for my studies.
3 | As a user, I want to have a feedback portal so that I can chare my comments.
4 | As a user, I want to be able to see the recorded success stories so that it can help me know how successful this university's outcome is.
5 | As a user, I want to be able to see the recorded hours thought so that it can help me know how active this university's teaching is.
6 | As a user, I want to be able to see the recorded active students so that it can help me know how many active students the university has.
7 | As a user, I want to have information about covid-19 so that I can keep myself safe.
8 | As a user, I want to be able to see the links with labels so that it can help me in the usage of the links.
9 | As a user, I want to see videos so that I can understand majors better.